BlackHand OS

Project Status & Onboarding Briefing

March 2026  ·  Prepared for Team Review

# Executive Summary

BlackHand OS is an ambitious custom mobile operating system and hardware project with a clearly defined multi-phase roadmap. The project targets a fully custom phone experience: a bespoke embedded Linux OS running on Raspberry Pi 4 hardware today, and eventually migrating to a custom NXP-based PCB phone.

The project is in a strong intermediate state. Phase 1 (bare-metal FreeRTOS on STM32) is fully complete. Phase 2 (Buildroot-based embedded Linux) has a working build system, a bootable SD card image, a custom display driver, and a substantially implemented UI framework — but backend services remain skeletal. With a new team member joining, now is the ideal time to divide the remaining work and accelerate toward a full integration milestone.

| Project Area | Status | Completion % |
| --- | --- | --- |
| Phase 1 — STM32 FreeRTOS | ✅ Complete | 100% |
| Build System (Buildroot) | ✅ Functional | 95% |
| Display / HW Bring-up | ✅ Complete | 90% |
| UI Framework (screens) | 🟡 Substantial (9/11) | 75% |
| Backend Services | ❌ Mostly Stubs | 10% |
| IPC / Service Mesh | ❌ Not Started | 5% |
| Init System (PID 1) | ❌ Not Started | 5% |
| Documentation | 🟡 Partial | 40% |

# 1. What Is Implemented

## 1.1  Phase 1 — STM32F429 + FreeRTOS

Phase 1 is fully complete. It served as the embedded systems foundation and learning milestone before moving to Linux. The implementation includes:

- ARM Cortex-M4 bare-metal bring-up (STM32F429I Discovery board)

- Full FreeRTOS v10.x integration with tasks, queues, semaphores, and timers

- Peripheral drivers: UART, GPIO, I2C, SPI, ADC, DMA, TIM

- CMSIS (ARM) library headers fully integrated

- OpenOCD + GDB debugging pipeline configured

## 1.2  Build System & Board Configuration

The Buildroot BR2_EXTERNAL tree is complete and functional. It covers the entire OS build pipeline from source to bootable image.

- blackhand_pi4_defconfig — Raspberry Pi 4 target configuration

- 9 custom Buildroot packages defined (Config.in + .mk files for each)

- post-build.sh and post-image.sh hook scripts

- genimage.cfg for SD card image layout

- Docker-based build environment (Dockerfile present)

- sdcard.img — 385 MB bootable image already built and on disk

NOTE A working bootable image already exists. The current gap is not build infrastructure — it is the C code inside each service package.

## 1.3  Display & Hardware Bring-up

- HyperPixel 4.0 display (800×480 DPI touch) fully configured

- Device tree overlays written and integrated into Buildroot

- Touch input calibration setup

- Linux kernel 6.6+ configuration tuned for Pi 4

- Init scripts (rcS, rcK) in /etc/init.d/ for BusyBox init

## 1.4  UI Framework — blackhand-ui (~8,800 Lines of C)

This is the most substantial body of completed work. The UI application is a terminal-graphics app powered by Notcurses running fullscreen on the HyperPixel display.

| Screen | File | Lines | Status |
| --- | --- | --- | --- |
| Home / Launcher | screen_home.c | 619 | ✅ Implemented |
| Settings | screen_settings.c | 599 | ✅ Implemented |
| Notes Editor | screen_notes.c | 610 | ✅ Implemented |
| Music Player | screen_mp3.c | 559 | ✅ Implemented |
| Voice Memos | screen_voice_memo.c | 572 | ✅ Implemented |
| Contacts | screen_contacts.c | 403 | ✅ Implemented |
| Alarms | screen_alarm.c | 381 | ✅ Implemented |
| Theme Picker | screen_theme.c | 77 | ✅ Implemented |
| Calls | screen_calls.c | 164 | 🟡 Placeholder shell |
| Messages (SMS) | screen_messages.c | 164 | 🟡 Placeholder shell |
| Bluetooth | screen_bluetooth.c | 42 | ❌ Disabled stub |

The UI layer also has a mature service library:

| Service | Responsibility | Status |
| --- | --- | --- |
| mp3_service | MPG123 music playback, library scan | ✅ ~705 lines |
| notes_service | File I/O, markdown, list management | ✅ Implemented |
| contacts_service | Contact CRUD, storage | ✅ Implemented |
| voice_memo_service | WAV record/playback, duration display | ✅ Implemented |
| alarm_service | Alarm management, time handling | ✅ Implemented |
| settings_service | Persistent settings (volume, brightness) | ✅ Implemented |
| theme_service | Color theming, contrast calculation | ✅ Implemented |
| multitap_service | T9 phone-style text input (0-9 keys) | ✅ Implemented |
| pin_service | PIN code auth | ✅ Implemented |
| comm_service | Backend IPC bridge | 🟡 Partial |
| bluetooth_service | Bluetooth stack integration | ❌ Stub only |

Core infrastructure components:

- main.c (891 lines) — event loop, screen routing, frame rendering orchestration

- config.h (283+ lines) — centralized colors, layout constants, string literals

- frame_renderer.c (303 lines) — status bar (time, battery %, signal bars), border drawing

- keypad_renderer.c (251 lines) — T9 input overlay visualization

- draw_utils.c (232 lines) — reusable text and shape drawing helpers

# 2. What Is In Progress

## 2.1  comm_service — IPC Bridge

comm_service.c is a partially built bridge between the UI layer and the backend service processes. It exists and compiles, but the actual socket connection logic and JSON-RPC message dispatch are not implemented. The UI currently runs with simulated/hardcoded data rather than real backend calls.

## 2.2  Calls & Messages Screens

screen_calls.c and screen_messages.c both exist at ~164 lines each. They contain the screen scaffolding (navigation, layout rendering) but have no real functionality — they are waiting for the modem backend service to be implemented before they can be wired up.

## 2.3  Hardware Abstraction Layer (platform/hardware.c)

The battery percentage and cellular signal values displayed in the status bar are currently simulated with placeholder values. The stubs are clearly marked and are waiting for real hardware integration (modem AT commands for signal, ADC/fuel gauge for battery).

# 3. What Needs to Be Done

The following components are nearly empty stubs (<30 lines of placeholder code each). These represent the primary development effort remaining.

## 3.1  blackhand-init — Custom PID 1 Init System

Current state: 17 lines of comments and function stubs. This is the most foundational missing piece — nothing else can run properly without a working init system.

What must be built:

- Mount virtual filesystems at boot (/proc, /sys, /dev, /run, /tmp)

- Spawn all service processes in correct dependency order

- Install SIGCHLD handler to reap zombie processes

- Basic crash recovery / service restart logic

- Clean shutdown sequence on poweroff/reboot signals

Estimated effort: ~500–700 lines of C. This is Level 3 on the roadmap.

## 3.2  blackhand-ipc — Inter-Process Communication Library

Current state: 11 lines. This library provides the communication backbone that lets all services talk to each other and to the UI.

What must be built:

- Unix domain socket server creation and connection handling

- JSON-RPC 2.0 message framing and parsing

- Request/response routing with method dispatch table

- Async event broadcasting (for UI to receive real-time updates)

Estimated effort: ~1,000–1,500 lines of C. Foundational dependency — audio, modem, storage all sit on top of this.

## 3.3  blackhand-audio — ALSA Audio Service

Current state: 13 lines across 3 files. The UI music player and voice memo screens are fully built — they are just waiting for this service to be real.

What must be built:

- ALSA PCM capture pipeline for voice recording

- ALSA PCM playback pipeline for music/memo output

- MPG123 integration for MP3 decoding (already used in mp3_service.c in the UI — needs backend counterpart)

- Volume control via ALSA mixer API

- JSON-RPC interface exposed over IPC socket

Estimated effort: ~1,500–2,000 lines of C.

## 3.4  blackhand-stt — Speech-to-Text Service

Current state: 4 lines. The voice memo screen exists in the UI; this service adds transcription.

What must be built:

- Integrate Vosk (recommended — fully offline, small model) or Whisper.cpp

- Stream audio from blackhand-audio service

- Return transcription results over IPC

- SQLite persistence of transcribed text (schema.sql already exists)

Estimated effort: ~2,000–3,000 lines of C/C++. Vosk has a C API; Whisper.cpp requires C++ wrappers.

## 3.5  blackhand-modem — Cellular Modem Service

Current state: 15 lines across 3 files. This service unlocks the Calls and Messages screens entirely.

What must be built:

- AT command parser for sending/receiving modem commands over serial

- Call control: dial, answer, hangup, DTMF

- SMS: send, receive, PDU decode

- Signal strength polling (feeds the hardware.c status bar stub)

- Audio path switching (microphone/speaker routing during calls)

Estimated effort: ~1,000–1,500 lines of C. Requires a compatible USB LTE modem (e.g., SIM7600, Quectel EC25).

## 3.6  blackhand-storage — SQLite Database Service

Current state: 4 lines + schema.sql. The schema is already designed — notes, contacts, and alarms currently use flat files in the UI services. This service centralizes them in SQLite.

What must be built:

- SQLite3 database initialization and migration system

- CRUD operations for notes, contacts, alarms, voice memo metadata, SMS

- JSON-RPC interface for queries and writes

- Transaction support for atomic multi-table writes

Estimated effort: ~500–800 lines of C.

## 3.7  Bluetooth Service

Current state: stub header, explicitly marked as deferred. The UI screen is disabled.

Future scope: BlueZ D-Bus integration, A2DP audio profile for wireless headphones, phone book access profile (PBAP).

## 3.8  Documentation

Two key documentation files (architecture.md and build-guide.md) exist as 4-line stubs. For a new team member, these are high-priority to write early.

- architecture.md — system diagram, service dependency graph, IPC message flows

- build-guide.md — step-by-step build environment setup, common errors, flashing instructions

- ipc-protocol.md — document the JSON-RPC schema for each service

# 4. Recommended Path Forward

## 4.1  Immediate Priority: Unblock the Foundation

Before any feature work can be validated end-to-end, the IPC layer and init system must exist. Everything depends on them. These two items should be the first sprint.

PRIORITY 1 Build blackhand-ipc first. Design the JSON-RPC socket protocol, write the library, and write a simple test client/server pair. Every other service will be built on top of this.

PRIORITY 2 Build blackhand-init next. Even a minimal PID 1 that mounts filesystems and launches services in sequence is enough to unblock integration testing.

## 4.2  Suggested Team Split (Two Developers)

With a new team member joining, the work divides naturally along two tracks that can proceed in parallel after the IPC foundation is in place:

| Track | Owner Suggestion | Work Items |
| --- | --- | --- |
| Track A — OS Core | Original developer | blackhand-init, blackhand-ipc, blackhand-storage, system integration & testing |
| Track B — Services & Features | New team member | blackhand-audio, blackhand-stt, blackhand-modem, Calls/Messages UI wiring, documentation |

Track A requires deeper familiarity with the existing codebase and its architecture decisions. Track B is well-scoped for onboarding because the UI screens already define exactly what each service needs to deliver — the contract is clear.

## 4.3  Sprint-by-Sprint Roadmap

| Sprint | Goals | Deliverable |
| --- | --- | --- |
| Sprint 1 (1–2 wk) | IPC library + init system foundation | Services launch and communicate over sockets |
| Sprint 2 (2 wk) | Audio service + storage service | Music player and voice memos use real backend |
| Sprint 3 (2 wk) | Modem service + AT parser | Outgoing calls working; SMS send/receive |
| Sprint 4 (1–2 wk) | STT integration (Vosk) | Voice memos auto-transcribed |
| Sprint 5 (2 wk) | Calls/Messages UI wired to modem | Full call flow functional on device |
| Sprint 6 (1 wk) | Hardware HAL (battery, signal real data) | Status bar shows real values |
| Sprint 7 (2 wk) | System hardening, OverlayFS rootfs | Read-only rootfs; crash-safe storage |
| Sprint 8 (ongoing) | Phase 3 planning — custom PCB design | NXP SoC selection, schematic start |

## 4.4  For the New Team Member — Onboarding Checklist

Start here in order:

- Read README.md and Phases.md cover-to-cover — they are well-written and explain the project philosophy and goals

- Read UI_LOGIC_CHECKLIST.md — this defines the expected behavior of every screen feature

- Set up the Docker build environment (Phase-2/docker/Dockerfile) and build the sdcard.img

- Flash the image to an SD card and boot the Pi 4 to see the current UI in action

- Read main.c to understand the event loop, then trace one screen (e.g. screen_notes.c + notes_service.c) end to end

- Read the IPC protocol spec (ipc-protocol.md) once it is drafted — this defines your service interface

- Pick up Track B work items from Section 4.2 above

# 5. Technical Reference

## 5.1  Technology Stack

| Layer | Technology | Notes |
| --- | --- | --- |
| Hardware (dev) | Raspberry Pi 4 + HyperPixel 4.0 | 800×480 DPI touchscreen, DPI interface |
| Hardware (target) | Custom NXP SoC PCB | Phase 3 — future |
| Build System | Buildroot + BR2_EXTERNAL | Custom package tree, Pi 4 defconfig |
| Linux Kernel | 6.6+ (custom .config) | Minimal, device-specific |
| Init System | Custom C (blackhand-init) | Replaces BusyBox init |
| IPC | Unix domain sockets + JSON-RPC 2.0 | Framed messages per service |
| UI Graphics | Notcurses library | Terminal graphics fullscreen on HyperPixel |
| Audio | ALSA + MPG123 + libsndfile | Playback and capture |
| STT Engine | Vosk (planned) | Offline, low-resource C API |
| Database | SQLite 3 | schema.sql already defined |
| Modem | AT commands over serial TTY | USB LTE modem target |
| Languages | C (primary), Shell | Some C++ for Whisper.cpp if chosen |

## 5.2  Key File Reference

| File | Purpose | Lines |
| --- | --- | --- |
| Phase-2/blackhand-external/package/blackhand-ui/src/main.c | Main event loop — start here | 891 |
| Phase-2/blackhand-external/package/blackhand-ui/src/ui.h | Screen enum & all declarations | 273 |
| Phase-2/blackhand-external/package/blackhand-ui/src/config.h | All colors, layout, string constants | 283 |
| Phase-2/blackhand-external/package/blackhand-ui/src/frame_renderer.c | Status bar & border rendering | 303 |
| Phase-2/blackhand-external/package/blackhand-ui/src/keypad_renderer.c | T9 keypad overlay | 251 |
| Phase-2/blackhand-external/package/blackhand-init/src/init.c | PID 1 stub — implement this first | 17 |
| Phase-2/blackhand-external/package/blackhand-ipc/src/ipc.c | IPC library stub — implement second | 11 |
| Phase-2/blackhand-external/configs/blackhand_pi4_defconfig | Buildroot board config | — |
| Phase-2/blackhand-external/docs/ipc-protocol.md | IPC protocol spec — needs filling in | — |
| Phase-2/UI_LOGIC_CHECKLIST.md | 200+ item UI test checklist | 200+ |
| README.md | Project overview & goals | 530 |
| Phases.md | Full phase roadmap | 1000+ |

## 5.3  Estimated Code Volume Remaining

| Component | Est. Lines | Priority |
| --- | --- | --- |
| blackhand-ipc (IPC library) | 1,000–1,500 | 🔴 Critical |
| blackhand-init (init system) | 500–700 | 🔴 Critical |
| blackhand-audio (ALSA service) | 1,500–2,000 | 🟠 High |
| blackhand-modem (AT + SMS + calls) | 1,000–1,500 | 🟠 High |
| blackhand-storage (SQLite service) | 500–800 | 🟠 High |
| blackhand-stt (Vosk/Whisper) | 2,000–3,000 | 🟡 Medium |
| Calls & Messages UI completion | 500–800 | 🟡 Medium |
| Hardware HAL (battery, signal) | 200–400 | 🟡 Medium |
| Bluetooth service | 1,000–2,000 | ⚪ Low / Deferred |
| Documentation | N/A | 🟠 High |
| TOTAL REMAINING | ~8,000–13,000 |  |

# 6. Overall Assessment

BlackHand OS is a well-conceived, well-documented project with a strong foundation. The UI layer is genuinely impressive — ~8,800 lines of C that implements a complete phone interface with T9 input, theming, music playback, voice memos, notes, contacts, and alarms. The build system is professional-grade.

The gap is the service layer. The Buildroot packages for init, IPC, audio, modem, and storage are stubs with fewer than 15 lines each. These are not half-finished — they are blank slates waiting to be built. This is not a problem; it is a natural consequence of building the UI first to validate the user experience before implementing the backend.

With two developers, this project is well-positioned to reach full integration within 3–4 months. The architecture is sound, the roadmap is detailed, and the existing code quality (well-commented, modular, consistent naming) makes onboarding straightforward.

BOTTOM LINE The project is approximately 40% complete by code volume, but the hardest architectural decisions have already been made and the most user-facing work is done. The remaining work is implementation of well-defined backend services following an established pattern.